## Sheet1
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FOURTH QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
I) Social Development
1. Installation of Streetlights | Pattaui-Pallua Road, | 16502000 | Upon Approval | 180 Calendar | 82.93% | 13684695.8 | - | on going
| Taguinod Street, |  |  | Days
Atulayan Sur-Linao East,
By Pass Road Carig Sur/
Caggay
2. Potable Water System | City Wide | 400000 | Upon Approval | 354 Calendar | 87.43% | 349716 | - | on going
3. Upgrading of Tuguegarao City People's | Centro 6 | 4400000 | Upon Approval | 180 Calendar | 47.24% | 2078344.33 | - | on going
General Hospital |  |  |  | Days
4. Health Centers-Health Facility | San Gabriel | 5500000 | Upon Approval | 120 Calendar | 99.73% | 5484925.39 | - | 100%
Enhancement |  |  |  | Days
5. Construction of Multi-Purpose Building | Enrile Boulevard, | 10000000 | Upon Approval | 270 Calendar | 0% | 0 | - | -
| Carig Sur |  |  | Days
Realignment
pursuant to
JMC No.1 dated
March 27,2020
6. COVID-19 PPAs-Related Expenses | City Wide | 36656000 | Upon Approval | 270 Calendar | 82.34% | 30182514.3 | - | on going
Days
-Supplies (Hospital Supplies) | Realignment | 7684000 |  |  |  | 2612750
-Home Accomodation | pursuant to | 4050000 |  |  |  | 4025700
-Meals and Snacks | JMC No.1 dated | 19122000 |  |  |  | 19115759
-Relief Goods | March 27,2020 | 3538000 |  |  |  | 3137385.3
-Disinfecting Supplies and Materials |  | 350000 |  |  |  | 141120
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FOURTH QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
-Misting Machine |  | 562000 |  |  |  | 562000
-Knapsack Spray |  | 750000 |  |  |  | 450000
-Decontamination Tent |  | 0 |  |  |  | 0
-Thermal Scanner |  | 600000 |  |  |  | 137800
II. Economic Management Development
1. Road Opening | Bartolome Street, Caggay | 0 | Upon Approval | 45 Calendar | 0% | 0 | - | -
| Realignment |  |  | Days
pursuant to
JMC No.1 dated
March 27,2020
2. Road Concreting | San Gabriel and | 4521000 | Upon Approval | 90 Calendar | 99.11% | 4480793.25 | - | 100%
| Cataggaman Nuevo |  |  | Days
3. Upgrading/Improvement/ | Ipil-Ipil Street , | 7600000 | Upon Approval | 120 Calendar | 97.04% | 7374902.26 | - | 100%
Rehabilitation of Slaughterhouse | Capatan |  |  | Days
4. Construction of Auction Market | Gosi Norte | 5469477 | Upon Approval | 150 Calendar | 91.52% | 5005566.56 | - | -
Days
5. Upgrading/Demolition and | Balzain East | 0 | Upon Approval | 180 Calendar | 0% | 0 | - | on going
Reconstruction of Don Domingo Public | Realignment |  |  | Days
Market | pursuant to
JMC No.1 dated
March 27,2020
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FOURTH QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
6. Maintenance of Road Asphalt Overlay | Along Arellano Street | 17774901 | Upon Approval | 180 Calendar | 99% | 17597162.67 | - | 100%
| (Mabini to Bassig Streets) |  |  | Days
Along Arellano Street
(Rizal to Mabini Streets)
III. Environmental Management
1. Construction of Masonry Drainage | Along Lecaros Street, | 26237700 | Upon Approval | 150 calendar | 77.61% | 20362545.61 | - | on going
| Extention, Ugac Sur |  |  | days
Along Arellano Street,
Ugac Sur
Along Montessory Street ,
Leonarda
Along Sanit Louis Village,
Ugac Sur
Along Avida Outlet,
Carig Sur
Along Arao Street,
Ugac Sur
Along Tobias Street,
Ugac Sur
Along Carag Street,
Leonarda
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FOURTH QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
Cagayan National High
School
Along Provincial Road
Atulayan Norte
Along San Roque Street,
Pengue-Ruyu
Total |  | 135061078 |  |  | 78.93% | 106601166.17
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Sgd. POTENCIANA I. CAMPOS |  |  |  | Sgd. ATTY. JEFFERSON P. SORIANO
City Budget Officer |  |  |  | City Mayor
0