## Sheet1
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
SECOND QUARTER 2021
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
I) Social Development
1. Installation of Streetlights | Campos Street and | 7904210 | Upon Approval | 180 calendar | 0% | 0 | - | Bid out
| Rizal coner Gomez Streets |  |  | days |  |  |  | documents on
process
2. Construction of Multi-Purpose | Carig Sur | 20000000 | Upon Approval | 300 calendar | 0% | 0 | - | 0%
Building |  |  |  | days
II. Economic Management Development
1. Road Opening | Tuguegarao By Pass | 11579490 | Upon Approval | 300 calendar | 0% | 0 | - | 0%
| Road-Bartolome Street, |  |  | days
Caggay
2. Road Concreting | Namabbalan Sur, | 23574322 | Upon Approval | 300 calendar | 35.46% | 8359620.52 | - | ON GOING
| Tanza, Pallua Sur, |  |  | days
Gosi Norte, Leonarda,
Cataggaman Viejo,
Ugac Norte, Tanza,
Caggay,Pallua Sur,
Carig Sur
3. Completion of Slaughtherhouse | Capatan | 3363779 | Upon Approval | 180 calendar | 0% | 0 | - | 0%
days
4. Completion of Auction Market | Gosi | 5465570 | Upon Approval | 180 calendar | 0% | 0 | - | Bid out
|  |  |  | days |  |  |  | documents on
process
5. Four Wheeled Drive Tractor | City Government | 3500000 | Upon Approval | 2nd Quarter | 0% | 0 | - | Bid out
documents on
process
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
SECOND QUARTER 2021
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
6. Maintenance of Road Asphalt Overlay | Along Del Rosario | 30231000 | Upon Approval | 60 calendar days | 0% | 0 | - | Bid out
| Street (Lecaros Street | [6 empty] | documents on
| to College Avenue) and | [6 empty] | process
Along Magallanes
Street (Lecaros Street
to Legaspi Street)
III. Environmental Management
1. Construction of Masonry Drainage | Libag Norte, | 22689113 | Upon Approval | 300 calendar | 11.42% | 2590314.08 | - | on going
| Tanza,Pallua Sur, |  |  | days
San Gabriel,
Pengue Ruyu,
Cataggaman Pardo,
Capatan and Ugac Sur
2. Construction of MRF | Demo Farm, Lingaling, | 2000000 | Upon Approval | 120 calendar | 0% | 0 | - | Bid out
| Gosi Norte |  |  | days |  |  |  | documents on
process
3. Construction and Heavy Equipment | Tuguegarao City
-Garbage Compactor |  | 10000000 | Upon Approval | 300 calendar | 99.9% | 9990000 | - | 100%
-Dumptruck |  | 3734300 |  | days |  |  |  | documents on
process
TOTAL |  | 144041784 |  |  | 14.54% | 20939934.6
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
POTENCIANA I. CAMPOS |  |  |  | ATTY. JEFFERSON P. SORIANO
City Budget Officer |  |  |  | City Mayor