## TFU Q2 2021 (2)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
AS OF 2nd QUARTER, CY 2021
City: TUGUEGARAO
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
FINANCIAL ASSISTANCE FOR MEALS OF COVID 19 POSITIVE PATIENTS WHO ARE ADMITTED IN TWO ISOLATION UNITS 120 BED CAPACITY FOR 60 DAYS (MTWD) | Tuguegarao City | 800000 | 2021-06-11 | 12-31-21 | 0% | 0 |  | Not Yet Implemented
ELIGIBLE HEALTH WORKERS ENTITLED TO MEALS AND ACCOMODATION (DOH) | Tuguegarao City | 257238.66 | 2021-05-26 | 12-31-21 | 100% | 257238.66 |  | Fully Implemented
Cataggaman Riverpark at Brgy. Cataggaman Nuevo(LGSF-AC FY 2020 GAA, RA11465) | along Pinacanauan National Tuguegarao Avenue, Tuguegarao City | 12104934 | 2021-05-24 |  | 0% | 0 |  | Not Yet Implemented
Support to the Cagayan Valley Smarter Belt for LGU - Tuguegarao City (DOST) | Tuguegarao City | 1000000 | 2021-05-03 | 12-31-21 | 0% | 0 |  | Not Yet Implemented
Completion of Tuguegarao City Urban Health Center, San Gabriel, Tuguegarao City (PB-INF-2020-043) DOH | Tuguegarao City Urban Health Center, San Gabriel, Tuguegarao City ( | 3940000 | 2021-04-30 | 12-31-21 | 99.98% | 3939028.03 |  | Fully Implemented
URBAN AGRICULTURAL PROJECT KNOWN AS "BAYANIHAN TO RECOVER AS ONE ACT" (DA) | City Demo Farm, Gosi Norte, Tuguegarao City | 3000000 | 2021-03-22 | 12-31-21 | 99.53% | 2985787.81 |  | Fully Implemented
Payment of honoraria of BAC members for 2021 | Tuguegarao City | 421000 | 2021-02-24 | 12-31-21 | 49.93% | 210200 |  | Partially Implemented
Recovery and reconstruction of the economy and livelihood in the LGUs that are directly affected by Taal Volcano eruption, Typhoon Quinta, Rolly and Ulysses chargeble against the FY 2021 LGSF- Disater Reduction and Rehabilitation Assistance Program, FY2021 GAA RA No. 11518 | Tuguegarao City | 31906858 | 2021-02-23 |  | 0% | 0 |  | Not Yet Implemented
FINANCIAL ASSISTANCE TO COVID 19 RESPONSE (DOH) | Tuguegarao City | 2000000 | 2020-12-28 |  | 13.28% | 265585 |  | Partially Implemented
Payment of Special Risk Allowance (SRA) Active Hazard Duty Pay of medical health workers(AHDP) (DOH) | City Health Office and Tuguegarao City Peoples General Hospital | 6543213.26 | 2020-12-23 |  | 100% | 6543213.26 |  | Fully Implemented
FINANCIAL ASSISTANCE (Immediate Needs of people affected by Typhoons Quinta, Rolly, Siony and Ulysses) | Tuguegarao City | 5000000 | 2020-12-09 |  | 63.47% | 3173420 |  | Partially Implemented
NDRRM TRUST LIABILITY | Tuguegarao City | 23464014 | 2020-12-09 |  | 0% | 0 |  | Not Yet Implemented
Donation-Typhoon Ulysses | Tuguegarao City | 9265402.45 | 2020-11-17 |  | 74.69% | 6920040 |  | Partially Implemented
RESOLUTION FOR RE-ALIGNMENT FOR COVID 19 | Tuguegarao City | 5570331 | 2020-10-15 |  | 44.41% | 2473800 |  | Partially Implemented
For Livelihood Assistance Tupad BKBK and 45 Skilled workers Materials/Tools/Equipment | Tuguegarao City | 4712356 | 2020-07-10 |  | 100% | 4712356 |  | Fully Implemented
Pinacanauan River Park (Phase II) | along Pinacanauan National Tuguegarao Avenue, Tuguegarao City | 15231317 | 2020-05-11 |  | 0% | 0 |  | Not Yet Implemented
Social Amelioration Program (SAP) during Covid 19 Pandemic | Tuguegarao City | 140827500 | 2020-04-14 |  | 99.79% | 140525000 |  | Fully Implemented
Donation for COVID 19 | Tuguegarao City | 3929350 | 2020-03-23 |  | 98.76% | 3880515.9 |  | Fully Implemented
Supply and delivery of Solid Waste Management Equipment for Organic Fertilizers Production (DILG PERFORMANCE CHALLENGE FUND) | Tuguegarao City | 3500000 | 2020-01-21 |  | 94.29% | 3300000 |  | Fully Implemented
Payment of Tuguegarao City Commercial Center (Mall of the Valley "MOVA" )Globe Electric Bill | Tuguegarao City | 1093490.3 | 2019-07-11 |  | 0% | 0 |  | Partially Implemented
Pinacanauan River Park (Phase I) | along Pinacanauan National Tuguegarao Avenue, Tuguegarao City | 9652077 | 2019-06-26 |  | 99.67% | 9620452.22 |  | Fully Implemented
CASH PRIZE LOCAL HEALTH SYSTEM | Tuguegarao City | 50000 | 2019-05-11 |  | 0%
Installation of Street Lights | along Enrile Blvd. Carig Sur, Tuguegarao City | 5000000 | 2019-03-11 |  | 99.13% | 4956377.03 |  | Fully Implemented
40% share of LGUs in the proceeds of National Wealth particularly Tobacco excise taxes for FY 2016 GAA RA NO 10717 (Various) | Tuguegarao City | 32877012 | 2018-06-01 |  | 91.43% | 30060753.91 |  | Partially Implemented
40% share of LGUs in the proceeds of National Wealth particularly Tobacco Excise taxes for FY 2017 GAA RA NO 10924 (For Financial Support FY 2015 Collection) (Various) | Tuguegarao City | 11287596 | 2018-06-01 |  | 100% | 11287596 |  | Fully Implemented
20% OF FIRE CODE FEES | Tuguegarao City | 1546641.61 | 2017-08-11 |  | 84.41% | 1305468 |  | Partially Implemented
LGU share from the collection of Burley and Native Tobacco Excise Tax (Various) | Tuguegarao City | 20622197 | 2016-12-28 |  | 99.39% | 20495703.21 |  | Fully Implemented
BUB- Shared Service Facilities(SSF)-Mushroom Production | Tuguegarao City | 500000 | 2016-12-23 |  | 34.2% | 171000 |  | Partially Implemented
BUB- Yaman Pinoy | Tuguegarao City | 700000 | 2016-12-23 |  | 96.74% | 677172.5 |  | Fully Implemented
Shared Service facilities (SSF)-Support to SSF | Tuguegarao City | 500000 | 2016-12-23 |  | 74.81% | 374044.5 |  | Partially Implemented
City Share from the CY 2012 collection of Burley and Native Tobacco Excise Tax (Various) | Tuguegarao City | 10029060 | 2016-11-15 |  | 99.54% | 9982935.82 |  | Partially Implemented
BUB 2016-Integrated Community Food Production Integrated Cacao and Root Crops Production (Various) | Tuguegarao City | 500000 | 2016-07-01 | Continuing | 54.44% | 272184 |  | Partially Implemented
BUB- OTOP STORE | Tuguegarao City | 1500000 | 2016-05-20 |  | 90.72% | 1360779 |  | Fully Implemented
BUB- Industry Clustering Development Program (Cacao) | Tuguegarao City | 810000 | 2016-01-23 |  | 66.46% | 538355.02 |  | Partially Implemented
Payment of Hospital Bill of Indigent TCPGH patient (PCSO Endowement Fund ) | Tuguegarao City | 1000000 | 2015-10-01 | Continuing | 58.27% | 582705.41 |  | Partially Implemented
Pavvurulun Festival (Various) | Tuguegarao City | 4213021.81 | 2012-08-06 |  | 97.14% | 4092339.08 |  | Fully Implemented
PHIC Tuguegarao City Urban Health Center & Birthing - Honoraria of City Health Workers | Tuguegarao City | 3236760 | 2017 |  | 95.8% | 3100960 |  | Partially Implemented
PHIC Tuguegarao City Urban Health Center & Birthing - Hospital Charges | Tuguegarao City | 5646940 | 2017 |  | 30.44% | 1718897.59 |  | Partially Implemented
PhiHealth CATAGGAMAN NUEVO BIRTHING CENTER/HOSPITAL CHARGES | City Health Office, Tuguegarao City | 4791435.06 | 2014 |  | 45.71% | 2190262.32 |  | Partially Implemented
PhiHealth CATAGGAMAN NUEVO BIRTHING CENTER HONORARIA of City Health Workers | City Health Office, Tuguegarao City | 3245310 | 2014 |  | 98.86% | 3208317.5 |  | Partially Implemented
Payment of Social Pension Stipend of Indigent Senior Citizen of Tuguegarao City (DSWD) | Tuguegarao City | 95141100 | 2013 | Continuing | 100% | 95141100 |  | Fully Implemented
Payment of Tuguegarao City Commercial Center (Mall of the Valley "MOVA" )Water Bill | Tuguegarao City | 3032883.99 | 2011 |  | 97.04% | 2943211.31 |  | Partially Implemented
PhiHealth Capitation Fund for Tuguegarao City (Various) | City Health Office, Tuguegarao City | 18720003.7 | 2006 | Continuing | 82.46% | 15436584.02 |  | Partially Implemented
PhiHealth TB Dots for Tuguegarao City (Various) | City Health Office, Tuguegarao City | 3832200 | 2006 |  | 78.28% | 2999898.96 |  | Partially Implemented
Total |  | 445684462.18 |  |  |  | 351202288.43 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(sgd) JOSEPHINE B. NAGUI, CPA |  | (sgd) ATTY. JEFFERSON P. SORIANO
Local Accountant |  | Local Chief Executive