## Form 6 -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
3RD QUARTER, CY 2019
City: TUGUEGARAO
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
POTENCIANA I. CAMPOS |  | JOSEPHINE B. NAGUI, CPA |  |  |  | ATTY. JEFFERSON P. SORIANO
Local Budget Officer |  | Local Accountant |  |  |  | Local Chief Executive

## Form 6 -TFU Q4 2019
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
4TH QUARTER, CY 2019
City: TUGUEGARAO
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
| 2018 - Unexpended LDRRMF |  | 37556.61 | 2019-01-01 |  | 93.37% | 35066.88 |  | Partially Implemented
| 2017 - Unexpended LDRRMF |  | 1880301.46 | 2019-01-01 |  | 38.87% | 730866.2 |  | Partially Implemented
Donation during Typhoon Tisoy
| Theodor E. Stoops |  | 100000 | 2019-12-09 |  | 0% | 0 |  | Not Yet Implemented
| Landbank of The Philippines |  | 200000 | 2019-12-09 |  | 0% | 0 |  | Not Yet Implemented
| PCSO - Calamity Assistance |  | 1500000 | 2019-12-29 |  | 0% | 0 |  | Not Yet Implemented
Donation during Typhoon Ompong
| LGU of Makati City |  | 750000 | 2019-01-31 |  | 100% | 750000 |  | Fully Implemented
| LGU of Davao City |  | 10000 | Bal from 2018 |  | 100% | 10000 |  | Fully Implemented
| Provincial Govt of Davao Del Norte. |  | 500000 | 2018-09-28 |  | 100% | 500000 |  | Fully Implemented
| Provincial Govt of Compostela Valley |  | 16146 | Bal from 2018 |  | 100% | 16146 |  | Fully Implemented
| Provincial Govt of Davao Occidental |  | 500000 | 2018-10-01 |  | 100% | 500000 |  | Fully Implemented
| Landbank of The Philippines |  | 200000 | 2018-10-09 |  | 64.83% | 129669 |  | Partially Implemented
| City of Manila |  | 240000 | 2018-10-09 |  | 100% | 240000 |  | Fully Implemented
| Development Bank of the Philippines |  | 100000 | 2018-12-28 |  | 100% | 100000 |  | Fully Implemented
| Senator Grace Poe |  | 150000 | 2019-02-12 |  | 100% | 150000 |  | Fully Implemented
Donation during Typhoon Lawin
| LGU of Makati City |  | 200000 | 2016-10-24 |  | 0% | 0 |  | Not Yet Implemented
| LGU of Valenzuela City |  | 9885 | Bal from 2017 |  | 100% | 9885 |  | Fully Implemented
Donation during Typhoon Lando
| Land Bank of the Philippines |  | 1600 | Bal 2017 |  | 100% | 1600 |  | Fully Implemented
Donation during Typhoon Pedring & Quiel
| Land Bank of the Philippines - FA to areas affected by "Pedring & Quiel" |  | 4200 | Bal 2017 |  | 100% | 4200 |  | Fully Implemented
| Affiliation Fee - CHO |  | 18799 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| Affiliation Fee - PGH |  | 166832.8 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| BNEO - Barangay Newly Elected Officials 2018 |  | 48875.24 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| CAVRAA Sponsorship 2018 |  | 36000 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| DA ATI-RTC 02 Monetary Award of Corn Achievers for CY 2018 |  | 1025000 | 2019-02-11 |  | 84.79% | 869120.51 |  | Partially Implemented
| DBM - 20% Share from Collection of Fire Code Fees |  | 1270641.61 | Bal from 2018 |  | 12.75% | 162068 |  | Partially Implemented
| DBM - Share on Tobacco Excise Tax 2012 |  | 46124.18 | Bal 201 8 |  | 100% | 0 |  | Fully Implemented
| DBM - Share on Tobacco Excise Tax 2013 |  | 123893.79 | Bal 201 8 |  | 100% | 0 |  | Fully Implemented
| DBM (40% Share of LGU from Tobacco Excise Taxes for FY 2016 GAA, RA NO. 10717) |  | 15169190.58 | Bal from 2018 |  | 78.12% | 11850763.48 |  | Partially Implemented
| DBM-Kilos Asenso Program |  | 10038 | Bal from 2018 |  | 0% | 0 |  | Fully Implemented
| DENR PENRO - Bamboo Shoot Propagation |  | 3343.25 | Bal from 2018 |  | 0% | 0 |  | Fully Implemented
416-029-001 | DENR EMB Tug - (Fund Assistance for the Establishment of Public Market Ecological Solid Waste Management System) |  | 300000 | 2019-09-11 |  | 0% | 0 |  | Not Yet Implemented
| DepEd - Establishment of School Clinic | New Site, Carig Sur, Tug. City | 18267.1 | Bal Jan 1, 2018 |  | 99.54% |  |  | Fully Implemented
| DepEd - Establishment of School Library | Tuguegarao North Central School | 30036.74 | Bal 2018 |  | 99.54% |  |  | Fully Implemented
| DepEd - Provision of School Furniture | Secondary School of the SDO Tug. City | 3075 | Bal Jan 1, 2018 |  | 99.54% |  |  | Fully Implemented
416-016-2018-001 | DOF - Pinacanauan River Park along River Banks of Pinacanauan River | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 9652077 | 2019-06-26 |  | 0% | 0 |  | Not Yet Implemented
| DILG (2013 Performance Challenge Fund) |  | 3000000 | 2014-03-07 |  | 100% | 0 |  | Fully Implemented (Physically)
416-016-2018-001 | DOF - Pinacanauan River Park along River Banks of Pinacanauan River | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 9652077 | 2019-06-26 |  | 14.95% | 1443067.83 |  | Not Yet Implemented
| Don Domingo Stall Holders - Electric Bill for Temporary Location Sites | Don Domingo | 18679.5 | 2019-12-11 |  | 0% | 0 |  | Not Yet Implemented
| DOH - BUB-HFEP (CONSTRUCTION OF ANNAFUNAN BIRTHING CENTER AND TAGGA HEALTH STATION |  | 682.94 | Bal 2018 |  | 0% | 0 |  | Fully Implemented
| DOH Upgrading of Tuguegarao City Health Office & 10 Brgy Health Station under 2014 BUB Project |  | 2820292.13 | 2019 |  | 52.52% | 1481264.58 |  | Partially Implemented
| DOH-Repair & Improvement of Tuguegarao City Urban Health Center |  | 1531656.75 | 2018 Bal to 2019 |  | 0% | 0 |  | Partially Implemented
| DOLE -Starter Kit Financial Assistance-Livelihood Project |  | 1316700 | 2018-11-19 |  | 100% | 1316700 |  | Fully Implemented
| Donation for PEH |  | 7650 | Bal from 2017 |  | 0% | 0 |  | Fully Implemented
| DPWH SLRF Special Local Road Fund |  | 140.64 | 1/212018 |  | 0% | 0 |  | Fully Implemented
| DSWD BUB- Center as Temporary Shelter for CICL and VAWC |  | 31014.25 | Bal 2018 |  | 100% | 31014.25 |  | Fully Implemented
| DSWD Presidential Award for Child Friendly Municipalities and City (PACFMC) |  | 100000 | 2019-12-26 |  | 0% | 0 |  | Not Yet Implemented
| DSWD Child Friendly Program |  | 112156.05 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DSWD Senior Citizen Social Pension Program |  | 5314500 | 2019-01-01 |  | 100% | 5314500 |  | Fully Implemented
| DSWD Supplementary Feeding Program |  | 16151.57 | 2019-01-01 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Industry Clustering Development Program (Cacao) |  | 182916 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Shared Service Facilities (SSF)-Support to SSF |  | 169955.5 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTIBUB- Shared Service Facilities(SSF)-Mushroom Production |  | 329000 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Yaman Pinoy |  | 37287.5 | Bal 2018 |  | 38.78% | 14460 |  | Partially Implemented
| DTI-One Town One Product (OTOP) under LGSF FY 2016 GAA 10717 |  | 463806 | Bal 2018 |  | 25.85% | 119910 |  | Partially Implemented
| Fun Run |  | 89300 | 2019-02-28 |  | 37.18% | 33200 |  | Partially Implemented
| Jollibee Group Foundation BLT KITCHEN MODEL FOR DEPED SBFP |  | 265792.3 | Bal 2018 |  | 100% | 265792.3 |  | Fully Implemented
| Globe Electric Bill |  | 1093490.3 | Bal 2018 |  | 0% | 0 |  | Not Yet Implemented
| Mall of the Valley - water bill of stall holders |  | 424340.47 | 2019-01-01 |  | 74.81% | 317454.58 |  | Partially Implemented
| National Anti-Poverty Commission (NAPC) - Integrated Cacao and Root Crops Production |  | 227816 | Bal 2018 |  | 19.71% | 44900 |  | Partially Implemented
| National Nutrition Council |  | 45004.5 | Bal from 2017 |  | 0% | 0 |  | Partially Implemented
| Pavvurulun Festival |  | 1445912.73 | 2019 |  | 0% | 1185880 |  | Partially Implemented
| LGU OF ECHAGUE- FINANCIAL ASSISTANCE FOR AFI FESTIVAL | Tuguegarao City | 200000 | 2018-08-15 |  | 0% | 0 |  | Not Yet Implemented
| PCSO Endowment Fund for Indigent Patients | TCPGH | 1000000 |  |  | 59.5% | 595034.55 |  | Partially Implemented
| PHIC Capitation Fund |  | 5187174.08 | 2019-01-01 |  | 2.5% | 129688.02 |  | Partially Implemented
| PHIC Cattagaman Nuevo Birthing Center -Hospital Charges |  | 2932595.26 | 2019-01-01 |  | 3.729% | 109353.03 |  | Partially Implemented
| PHIC TB Dots |  | 843501.04 | 2019-01-01 |  | 1.091% | 9200 |  | Partially Implemented
| PHIC TugCity Urban Health Center & Birthing Hospital Charges |  | 3319235.11 | 2019-01-01 |  | 11.03% | 366008.95 |  | Partially Implemented
| PHIC TugCity Urban Health Center & Birthing PF/Honoraria City Health Workers |  | 869650 | 2019-01-01 |  | 77.47% | 673690 |  | Partially Implemented
| Phil Health Insurance Corp Service Fee |  | 220811.99 | 2018-03-07 |  | 0% | 0 |  | Partially Implemented
| Philhealth Professional Fee from Medicare Patients (POOL) | TCPGH | 15746517 | 2019-05-28 |  | 83.14% | 13091291 |  | Partially Implemented
| Philhealth Professional Fee from Private Patients (PRIVATE) |  | 13771832.17 | 2019-05-28 |  | 65.92% | 9077824 |  | Partially Implemented
| Professional Fee of Private Doctors |  | 13771832.17 | 2019-06-30 |  | 65.92% | 9077824 |  | Partially Implemented
| 2% Hospital Admin Cost for TCPGH | TCPGH | 600268.71 | 2019-06-30 |  | 15.53% | 93220 |  | Partially Implemented
| Philhealth Paid Package / PHIC - Professional Fee of DRs | TCPGH | 2222355.71 |  |  | 0% | 0 |  | Partially Implemented
| Philhealth Paid Package / PHIC - Refund to Patients | TCPGH | 10474397.24 |  |  | 0.05378% | 5633 |  | Partially Implemented
| Provincial Government of Cagayan - Road Concreting) | Dupaya Street at Brgy Leonarda) | 1000000 | 2019-03-11 |  | 93.35% | 933468.55 |  | Fully Implemented
| Provincial Government of Cagayan - Dumpsite, Tree Planting (Bamboo Shoots) | Pinacanauan River) | 3000000 | 2019-03-11 |  | 99.33% | 2979945.85 |  | Fully Implemented
| Provincial Government of Cagayan - Installation of Street lights | Enrile Boulevard, Carig Sur, Tuguegarao City | 5000000 | 2019-03-11 |  | 0% | 0 |  | Not Yet Implemented
| Regional Health Office 02 -Local Health System Award |  | 125000 | 2018-03-01 |  | 91.56% | 114450 |  | Partially Implemented
| ROPALI Sponsorship - TODA Seminar |  | 198000 | 2019-10-15 |  | 91.16% | 180500 |  | Partially Implemented
| Sale of Bid Documents |  | 1584410.24 | 2019-01-01 |  | 67.14% | 1063840.24 |  | Partially Implemented
| SK Federation Orientation and Election 2018 |  | 24390 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| TCTMG, PNP, FETODA, TODA |  | 804651.5 | 2019-01-01 |  | 27.76% | 223375 |  | Partially Implemented
| Total |  | 145914827.71 |  |  |  | 66351874.8 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| JOSEPHINE B. NAGUI, CPA |  | ATTY. JEFFERSON P. SORIANO
| Local Accountant |  | Local Chief Executive
Note on H51: a: mobilization fee plang ito

## TFU Q1 2020
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
1ST QUARTER, CY 2020
City: TUGUEGARAO
| Program or Project | Location | Total Cost/Beg Balance | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
| 2019 - Unexpended LDRRMF |  | 14790848.75 | 2020-01-01 |  | 0.5121% | 75750.01 |  | Partially Implemented
| 2017 - Unexpended LDRRMF |  | 1051935.26 | 2019-01-01 |  | 55.12% | 579775 |  | Partially Implemented
Donation during Typhoon Tisoy
| Theodor E. Stoops |  | 100000 | 2019-12-09 |  | 0% | 0 |  | Not Yet Implemented
| Landbank of The Philippines |  | 200000 | 2019-12-09 |  | 0% | 0 |  | Not Yet Implemented
| PCSO - Calamity Assistance |  | 1500000 | 2019-12-29 |  | 0% | 0 |  | Not Yet Implemented
Donation during Typhoon Ompong
| Landbank of The Philippines |  | 200000 | 2018-10-09 |  | 64.83% | 129669 |  | Partially Implemented
Donation during Typhoon Lawin
| LGU of Makati City |  | 200000 | 2016-10-24 |  | 0% | 0 |  | Not Yet Implemented
Donation during Typhoon Lando
Donation during Typhoon Pedring & Quiel
| Office of the President -FA (Immediate Needs of people affected by Typhoon Quiel and Ramon) |  | 5000000 | 2020-02-05 |  | 0% | 0 |  | Not Yet Implemented
Donation during COVID 19 Pandemic
| Donation during COVID 19 Pandemic |  | 200000 | 2020-03-23 |  | 0% | 0 |  | Not Yet Implemented
| Affiliation Fee - CHO |  | 18799 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| Affiliation Fee - PGH |  | 117311.8 | Bal 2019 |  | 11.8% | 13840 |  | Partially Implemented
| BNEO - Barangay Newly Elected Officials 2018 |  | 48875.24 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| CAVRAA Sponsorship 2018 |  | 36000 | Bal from 2019 |  | 0% | 0 |  | Partially Implemented
| DA ATI-RTC 02 Monetary Award of Corn Achievers for CY 2018 |  | 155879.49 | Bal from 2019 |  | 100% | 155879.49 |  | Fully Implemented
| DBM - 20% Share from Collection of Fire Code Fees |  | 1108573.61 | Bal from 2019 |  | 78.24% | 867400 |  | Partially Implemented
| DBM (40% Share of LGU from Tobacco Excise Taxes for FY 2016 GAA, RA NO. 10717) |  | 3318427.1 | Bal from 2019 |  | 15.13% | 502169.01 |  | Partially Implemented
| DBM ( Share of LGU's from the CY 2016 Collection of Burley Tobacco Exercise Taxes) |  | 4684933 | 2020-03-03 |  | 0% | 0 |  | Not Yet Implemented
| DBM-Kilos Asenso Program |  | 10038 | Bal from 2018 |  | 0% | 0 |  | Fully Implemented
| DENR PENRO - Bamboo Shoot Propagation |  | 3343.25 | Bal from 2018 |  | 0% | 0 |  | Fully Implemented
416-029-001 | DENR EMB Tug - (Fund Assistance for the Establishment of Public Market Ecological Solid Waste Management System) |  | 300000 | 2019-09-11 |  | 100% | 300000 |  | Fully Implemented
| DepEd - Establishment of School Clinic | New Site, Carig Sur, Tug. City | 18267.1 | Bal Jan 1, 2019 |  | 99.54% |  |  | Fully Implemented
| DepEd - Establishment of School Library | Tuguegarao North Central School | 30036.74 | Bal 2019 |  | 99.54% |  |  | Fully Implemented
| DepEd - Provision of School Furniture | Secondary School of the SDO Tug. City | 3075 | Bal Jan 1, 2019 |  | 99.54% |  |  | Fully Implemented
416-016-2018-001 | DOF - Pinacanauan River Park along River Banks of Pinacanauan River | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 9652077 | 2019-06-26 |  | 0% | 8181933.66 |  | Partially Implemented
| DILG (2019 Performance Challenge Fund) |  | 3500000 | 2020-01-21 |  | 0% | 0 |  | Not Yet Implemented
| DILG (2013 Performance Challenge Fund) |  | 3000000 | 2014-03-07 |  | 0% | 0 |  | Fully Implemented (Physically) Not Yet Financially
416-016-2018-001 | DOF - Pinacanauan River Park along River Banks of Pinacanauan River | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 9652077 | 2019-06-26 |  | 84.77% | 8181933.66 |  | Partially Implemented
| Don Domingo Stall Holders - Electric Bill for Temporary Location Sites | Don Domingo | 84054.5 | 2019-12-11 |  | 0% | 0 |  | Not Yet Implemented
| DOH - BUB-HFEP (CONSTRUCTION OF ANNAFUNAN BIRTHING CENTER AND TAGGA HEALTH STATION |  | 682.94 | Bal 2018 |  | 0% | 0 |  | Fully Implemented
| DOH-Repair & Improvement of Tuguegarao City Urban Health Center |  | 249840 | 2020 |  | 99.93% | 249666.57 |  | Fully Implemented
| Donation for PEH |  | 7650 | Bal from 2017 |  | 0% | 0 |  | Fully Implemented
| Donations For Nspc'S Programs And Activities) |  | 400000 | 2020-03-09 |  | 0% | 0 |  | Not Yet Implemented
| DPWH SLRF Special Local Road Fund |  | 140.64 | 1/212018 |  | 0% | 0 |  | Fully Implemented
| DSWD Presidential Award for Child Friendly Municipalities and City (PACFMC) |  | 100000 | 2019-12-26 |  | 0% | 0 |  | Not Yet Implemented
| DSWD Child Friendly Program |  | 112156.05 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DSWD Senior Citizen Social Pension Program |  | 0 | 0 |  | #DIV/0! | 0 |  | Fully Implemented
| DSWD Supplementary Feeding Program |  | 16151.57 | 2019-01-01 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Industry Clustering Development Program (Cacao) |  | 182916 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Shared Service Facilities (SSF)-Support to SSF |  | 169955.5 | Bal 2019 |  | 25.89% | 44000 |  | Partially Implemented
| DTIBUB- Shared Service Facilities(SSF)-Mushroom Production |  | 329000 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Yaman Pinoy |  | 37287.5 | Bal 2018 |  | 38.78% | 14460 |  | Partially Implemented
| DTI-One Town One Product (OTOP) under LGSF FY 2016 GAA 10717 |  | 329821 | Bal 2019 |  | 57.79% | 190600 |  | Partially Implemented
| Fun Run |  | 89300 | 2019-02-28 |  | 37.18% | 33200 |  | Partially Implemented
| Globe Electric Bill |  | 1093490.3 | Bal 2018 |  | 0% | 0 |  | Not Yet Implemented
| Mall of the Valley - water bill of stall holders |  | 106885.89 | 2019-01-01 |  | 72.31% | 77289.12 |  | Partially Implemented
| National Anti-Poverty Commission (NAPC) - Integrated Cacao and Root Crops Production |  | 227816 | Bal 2018 |  | 19.71% | 44900 |  | Partially Implemented
| National Nutrition Council |  | 45004.5 | Bal from 2017 |  | 0% | 0 |  | Partially Implemented
| Pavvurulun Festival |  | 173631.81 | Bal from 2019 |  | 0% | 149350 |  | Partially Implemented
| LGU OF ECHAGUE- FINANCIAL ASSISTANCE FOR AFI FESTIVAL | Tuguegarao City | 200000 | 2018-08-15 |  | 0% | 0 |  | Not Yet Implemented
| PCSO Endowment Fund for Indigent Patients | TCPGH | 404965.45 | Bal from 2019 |  | 0% | 0 |  | Partially Implemented
| PHIC Capitation Fund |  | 5057486.06 | 2020-01-01 |  | 0.7156% | 36190 |  | Partially Implemented
| PHIC Cattagaman Nuevo Birthing Center -Hospital Charges |  | 2823242.23 | 2020-01-01 |  | 0.7206% | 20343.6 |  | Partially Implemented
| PHIC TB Dots |  | 834301.04 | 2020-01-01 |  | 0.2397% | 2000 |  | Partially Implemented
| PHIC TugCity Urban Health Center & Birthing Hospital Charges |  | 3369476.16 | 2020-01-01 |  | 5.835% | 196625.65 |  | Partially Implemented
| PHIC TugCity Urban Health Center & Birthing PF/Honoraria City Health Workers |  | 402460 | 2019-01-01 |  | 40.06% | 161220 |  | Partially Implemented
| Phil Health Insurance Corp Service Fee |  | 220811.99 | 2018-03-07 |  | 0% | 0 |  | Partially Implemented
| Philhealth Professional Fee from Medicare Patients (POOL) | TCPGH | 4072688 | 2020-01-01 |  | 45.59% | 1856622 |  | Partially Implemented
| Philhealth Professional Fee from Private Patients (PRIVATE) |  | 2817982 | 2020-01-01 |  | 70.21% | 1978576 |  | Partially Implemented
| Professional Fee of Private Doctors |  | 10990499.07 | 2019-06-30 |  | 90.65% | 9963256.74 |  | Partially Implemented
| 2% Hospital Admin Cost for TCPGH | TCPGH | 873576.38 | 2019-06-30 |  | 0.07693% | 672 |  | Partially Implemented
| Philhealth Paid Package / PHIC - Professional Fee of DRs | TCPGH | 2222355.71 |  |  | 0% | 0 |  | Partially Implemented
| Philhealth Paid Package / PHIC - Refund to Patients | TCPGH | 10474397.24 |  |  | 0.05378% | 5633 |  | Partially Implemented
| Provincial Government of Cagayan - Road Concreting) | Dupaya Street at Brgy Leonarda) | 66531.45 | 2019-03-11 |  | 0% | 0 |  | Fully Implemented
| Provincial Government of Cagayan - Dumpsite, Tree Planting (Bamboo Shoots) | Pinacanauan River) | 20054.15 | 2019-03-11 |  | 0% | 0 |  | Fully Implemented
| Provincial Government of Cagayan - Installation of Street lights | Enrile Boulevard, Carig Sur, Tuguegarao City | 5000000 | 2019-03-11 |  | 84.99% | 4249533.81 |  | Partially Implemented
| Regional Health Office 02 -Local Health System Award |  | 125000 | 2018-03-01 |  | 91.56% | 114450 |  | Partially Implemented
| ROPALI Sponsorship - TODA Seminar |  | 198000 | 2019-10-15 |  | 91.16% | 180500 |  | Partially Implemented
| Sale of Bid Documents |  | 380000 | 2019-01-01 |  | 45.13% | 171500 |  | Partially Implemented
| SK Federation Orientation and Election 2018 |  | 24390 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| TCTMG, PNP, FETODA, TODA |  | 618476.5 | 2020-01-01 |  | 0% | 0 |  | Partially Implemented
| Total |  | 113852974.97 |  |  |  | 38728938.32 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| JOSEPHINE B. NAGUI, CPA |  | ATTY. JEFFERSON P. SORIANO
| Local Accountant |  | Local Chief Executive
Note on D10: a: QRF na ito ng STF - for Covid 19
Note on H43: a: mobilization fee plang ito

## TFU Q2 2020
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
2ND QUARTER, CY 2020
City: TUGUEGARAO
| Program or Project | Location | Total Cost/Beg Balance | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
| 2019 - Unexpended LDRRMF |  | 14790848.75 | 2020-01-01 |  | 11.2% | 1656240.27 |  | Partially Implemented
| 2017 - Unexpended LDRRMF |  | 1051935.26 | 2019-01-01 |  | 100% | 1051935.26 |  | Fully Implemented
Donation during Typhoon Tisoy
| Theodor E. Stoops |  | 100000 | 2019-12-09 |  | 0% | 0 |  | Not Yet Implemented
| Landbank of The Philippines |  | 200000 | 2019-12-09 |  | 0% | 0 |  | Not Yet Implemented
| PCSO - Calamity Assistance |  | 1500000 | 2019-12-29 |  | 99.7% | 1495500 |  | Fully Implemented
Donation during Typhoon Ompong
| Landbank of The Philippines |  | 70331 | Bal from 2019 |  | 0% | 0 |  | Partially Implemented
Donation during Typhoon Lawin
| LGU of Makati City |  | 200000 | 2016-10-24 |  | 0% | 0 |  | Not Yet Implemented
Donation during Typhoon Lando
Donation during Typhoon Pedring & Quiel
| Office of the President -FA (Immediate Needs of people affected by Typhoon Quiel and Ramon) |  | 5000000 | 2020-02-05 |  | 0% | 0 |  | Not Yet Implemented
Donation during COVID 19 Pandemic
| Donation during COVID 19 Pandemic |  | 3821750 | Jan-June 2020 |  | 13.51% | 516227.9 |  | Partially Implemented
| Donation during COVID 19 Pandemic - ABANA COMPUTER SERVICE |  | 27000 | 2020-04-03 |  | 100% | 27000 |  | Fully Implemented
| Affiliation Fee - CHO |  | 18799 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| Affiliation Fee - PGH |  | 117311.8 | Bal 2019 |  | 11.8% | 13840 |  | Partially Implemented
| BNEO - Barangay Newly Elected Officials 2018 |  | 48875.24 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| CAVRAA Sponsorship 2018 |  | 36000 | Bal from 2019 |  | 0% | 0 |  | Partially Implemented
| DBM - 20% Share from Collection of Fire Code Fees |  | 1108573.61 | Bal from 2019 |  | 78.24% | 867400 |  | Partially Implemented
| DBM (40% Share of LGU from Tobacco Excise Taxes for FY 2016 GAA, RA NO. 10717) |  | 3318427.1 | Bal from 2019 |  | 15.13% | 502169.01 |  | Partially Implemented
| DBM ( Share of LGU's from the CY 2016 Collection of Burley Tobacco Exercise Taxes) |  | 4684933 | 2020-03-03 |  | 0% | 0 |  | Not Yet Implemented
| DBM-Kilos Asenso Program |  | 10038 | Bal from 2018 |  | 0% | 0 |  | Fully Implemented
| DENR PENRO - Bamboo Shoot Propagation |  | 3343.25 | Bal from 2018 |  | 0% | 0 |  | Fully Implemented
416-029-001 | DENR EMB Tug - (Fund Assistance for the Establishment of Public Market Ecological Solid Waste Management System) |  | 300000 | 2019-09-11 |  | 100% | 300000 |  | Fully Implemented
| DepEd - Establishment of School Clinic | New Site, Carig Sur, Tug. City | 18267.1 | Bal Jan 1, 2019 |  | 99.54% |  |  | Fully Implemented
| DepEd - Establishment of School Library | Tuguegarao North Central School | 30036.74 | Bal 2019 |  | 99.54% |  |  | Fully Implemented
| DepEd - Provision of School Furniture | Secondary School of the SDO Tug. City | 3075 | Bal Jan 1, 2019 |  | 99.54% |  |  | Fully Implemented
416-016-2018-001 | DOF -Bureau of Treasury/LGSF Improvement of Local road | Along Blumentritt Street(Aguinaldo Street to lecaros Street), Tuguegarao Cit | 5000000 | 2020-06-01 |  | 0% | 0 |  | Not Yet Implemented
416-016-2018-001 | DOF - Pinacanauan River Park along River Banks of Pinacanauan River | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 9652077 | 2019-06-26 |  | 0% | 6738865.83 |  | Partially Implemented
416-016-2018-001 | DOF - Pinacanauan River Park (Phase II) along Pinacanauan National Tuguegarao Avenue, Tuguegarao City | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 15231317 | 2020-04-28 |  | 0% | 0 |  | Not Yet Implemented
| DILG - Performance Challenge Fund 2019 |  | 3500000 | 2020-01-21 |  | 0% | 0 |  | Not Yet Implemented
| DILG - Performance Challenge Fund 2013 | Bassig St., Ugac Sur, Tug. City | 3000000 | 2014-03-07 |  | 83.33% | 2500000 |  | Fully Implemented (Physically) Not Yet Financially
416-016-2018-001 | DOF - Pinacanauan River Park along River Banks of Pinacanauan River | Covering Brgys of Catg. Nuevo, Ugac Sur, Centro 9 and Balzain East All in Tug. City | 9652077 | 2019-06-26 |  | 84.77% | 8181933.66 |  | Partially Implemented
| Don Domingo Stall Holders - Electric Bill for Temporary Location Sites | Don Domingo | 84054.5 | 2019-12-11 |  | 0% | 0 |  | Not Yet Implemented
| DOH - BUB-HFEP (CONSTRUCTION OF ANNAFUNAN BIRTHING CENTER AND TAGGA HEALTH STATION |  | 682.94 | Bal 2018 |  | 0% | 0 |  | Fully Implemented
| DOH-Repair & Improvement of Tuguegarao City Urban Health Center |  | 249840 | 2020 |  | 99.93% | 249666.57 |  | Fully Implemented
| Donation for PEH |  | 7650 | Bal from 2017 |  | 0% | 0 |  | Fully Implemented
| Donations For Nspc'S Programs And Activities) |  | 400000 | 2020-03-09 |  | 0% | 0 |  | Not Yet Implemented
| DPWH SLRF Special Local Road Fund |  | 140.64 | 1/212018 |  | 0% | 0 |  | Fully Implemented
| DSWD Presidential Award for Child Friendly Municipalities and City (PACFMC) |  | 100000 | 2019-12-26 |  | 100% | 100000 |  | Fully Implemented
| DSWD Social Amelioration Program |  | 140827500 | 2020-04-13 |  | 99.79% | 140525000 |  | Fully Implemented
| DSWD Child Friendly Program |  | 112156.05 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DSWD Senior Citizen Social Pension Program |  | 18255000 | 0 |  | 97.83% | 17859000 |  | Fully Implemented
| DSWD Supplementary Feeding Program |  | 16151.57 | 2019-01-01 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Industry Clustering Development Program (Cacao) |  | 182916 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Shared Service Facilities (SSF)-Support to SSF |  | 169955.5 | Bal 2019 |  | 25.89% | 44000 |  | Partially Implemented
| DTIBUB- Shared Service Facilities(SSF)-Mushroom Production |  | 329000 | Bal 2018 |  | 0% | 0 |  | Partially Implemented
| DTI-BUB- Yaman Pinoy |  | 37287.5 | Bal 2018 |  | 38.78% | 14460 |  | Partially Implemented
| DTI-One Town One Product (OTOP) under LGSF FY 2016 GAA 10717 |  | 329821 | Bal 2019 |  | 57.79% | 190600 |  | Partially Implemented
| Fun Run |  | 89300 | 2019-02-28 |  | 37.18% | 33200 |  | Partially Implemented
| Globe Electric Bill |  | 1093490.3 | Bal 2018 |  | 0% | 0 |  | Not Yet Implemented
| Mall of the Valley - water bill of stall holders |  | 106885.89 | 2019-01-01 |  | 99.64% | 106497.32 |  | Partially Implemented
| National Anti-Poverty Commission (NAPC) - Integrated Cacao and Root Crops Production |  | 227816 | Bal 2018 |  | 19.71% | 44900 |  | Partially Implemented
| National Nutrition Council |  | 45004.5 | Bal from 2017 |  | 0% | 0 |  | Partially Implemented
| Pavvurulun Festival |  | 173631.81 | Bal from 2019 |  | 0% | 149350 |  | Partially Implemented
| PCSO Endowment Fund for Indigent Patients | TCPGH | 404965.45 | Bal from 2019 |  | 0% | 0 |  | Partially Implemented
| PHIC Capitation Fund |  | 5057486.06 | 2020-01-01 |  | 19.52% | 987085 |  | Partially Implemented
| PHIC Cattagaman Nuevo Birthing Center -Hospital Charges / CNBC-HC |  | 2823242.23 | 2020-01-01 |  | 1.465% | 41373.16 |  | Partially Implemented
| PHIC TB Dots |  | 834301.04 | 2020-01-01 |  | 0.2397% | 2000 |  | Partially Implemented
| PHIC TugCity Urban Health Center & Birthing Hospital Charges |  | 3622226.16 | 2020-01-01 |  | 14.67% | 531311 |  | Partially Implemented
| PHIC TugCity Urban Health Center & Birthing PF/Honoraria City Health Workers |  | 402460 | 2019-01-01 |  | 40.06% | 161220 |  | Partially Implemented
| Phil Health Insurance Corp Service Fee |  | 220811.99 | 2018-03-07 |  | 0% | 0 |  | Partially Implemented
| Philhealth Professional Fee from Medicare Patients (POOL) | TCPGH | 6800812 | 1/1/20-6/30/20 |  | 60.19% | 4093242 |  | Partially Implemented
| Philhealth Professional Fee from Private Patients (PRIVATE) |  | 5354702 | 1/1/20-6/30/20 |  | 69.73% | 3733619.6 |  | Partially Implemented
| Professional Fee of Private Doctors |  | 11387947.92 | 2019-06-30 |  | 99.58% | 11339681.74 |  | Partially Implemented
| 2% Hospital Admin Cost for TCPGH | TCPGH | 901463.18 | 2019-06-30 |  | 43.58% | 392828.85 |  | Partially Implemented
| Philhealth Paid Package / PHIC - Professional Fee of DRs | TCPGH | 2222355.71 |  |  | 0% | 0 |  | Partially Implemented
| Philhealth Paid Package / PHIC - Refund to Patients | TCPGH | 10474397.24 |  |  | 0.05378% | 5633 |  | Partially Implemented
| Provincial Government of Cagayan - Road Concreting) | Dupaya Street at Brgy Leonarda) | 66531.45 | 2019-03-11 |  | 0% | 0 |  | Fully Implemented
| Provincial Government of Cagayan - Dumpsite, Tree Planting (Bamboo Shoots) | Pinacanauan River) | 20054.15 | 2019-03-11 |  | 0% | 0 |  | Fully Implemented
| Provincial Government of Cagayan - Installation of Street lights | Enrile Boulevard, Carig Sur, Tuguegarao City | 5000000 | 2019-03-11 |  | 99.13% | 4956377.03 |  | Fully Implemented
| Regional Health Office 02 -Local Health System Award |  | 1730 | Bal from 2019 |  | 0% | 0 |  | Fully Implemented
| Regional Health Office 02 -Local Health System Award |  | 100000 | 2020-05-11 |  | 0% | 0 |  | Not Yet Implemented
| ROPALI Sponsorship - TODA Seminar |  | 198000 | 2019-10-15 |  | 91.16% | 180500 |  | Partially Implemented
| Sale of Bid Documents |  | 575000 | 2019-01-01 |  | 74% | 425500 |  | Partially Implemented
| SK Federation Orientation and Election 2018 |  | 24390 | Bal from 2018 |  | 0% | 0 |  | Partially Implemented
| TCTMG, PNP, FETODA, TODA |  | 618476.5 | 2020-01-01 |  | 0% | 0 |  | Partially Implemented
| Total |  | 302444653.13 |  |  |  | 210018157.2 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| JOSEPHINE B. NAGUI, CPA |  | ATTY. JEFFERSON P. SORIANO
| Local Accountant |  | Local Chief Executive
Note on D10: a: QRF na ito ng STF - for Covid 19
Note on H45: a: mobilization fee plang ito

## Sheet2
563847.5
967808.06
1531655.56