## Sheet1
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FIRST QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
I) Social Development
1. Installation of Streetlights | Pattaui-Pallua Road, | 16502000 | Upon Approval | 180 Calendar | 0% | 0 | - | -
| Taguinod Street, |  |  | Days
Atulayan Sur-Linao East,
By Pass Road Carig Sur/
Caggay
2. Potable Water System | City Wide | 400000 | Upon Approval | 354 Calendar | 0% | 0 | - | -
3. Upgrading of Tuguegarao City People's | Centro 6 | 4400000 | Upon Approval | 180 Calendar | 0% | 0 | - | -
General Hospital |  |  |  | Days
4. Health Centers-Health Facility | San Gabriel | 5500000 | Upon Approval | 120 Calendar | 27.63% | 1519883.88 | - | on going
Enhancement |  |  |  | Days
5. Construction of Multi-Purpose Building | Enrile Boulevard, | 30000000 | Upon Approval | 270 Calendar | 0% | 0 | - | -
| Carig Sur |  |  | Days
II. Economic Management Development
1. Road Opening | Bartolome Street, Caggay | 5000000 | Upon Approval | 45 Calendar | 0% | 0 | - | -
Days
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FIRST QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
2. Road Concreting | San Gabriel and | 4521000 | Upon Approval | 90 Calendar | 0% | 0 | - | -
| Cataggaman Nuevo |  |  | Days
3. Upgrading/Improvement/ | Ipil-Ipil Street , | 7600000 | Upon Approval | 120 Calendar | 0% | 0 | - | -
Rehabilitation of Slaughterhouse | Capatan |  |  | Days
4. Construction of Auction Market | Gosi Norte | 5469477 | Upon Approval | 150 Calendar | 0% | 0 | - | -
Days
5. Upgrading/Demolition and | Balzain East | 11656000 | Upon Approval | 180 Calendar | 0% | 0 | - | -
Reconstruction of Don Domingo Public |  |  |  | Days
Market
6. Maintenance of Road Asphalt Overlay | Along Arellano Street | 17774901 | Upon Approval | 180 Calendar | 0% | 0 | - | -
| (Mabini to Bassig Streets) |  |  | Days
Along Arellano Street
(Rizal to Mabini Streets)
III. Environmental Management
1. Construction of Masonry Drainage | Along Lecaros Street, | 26237700 | Upon Approval | 150 calendar | 1.083% | 284280.98 | - | on going
| Extention, Ugac Sur |  |  | days
Along Arellano Street,
Ugac Sur
FDP Form 7-20% Development Fund Utilization | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECT
FIRST QUARTER, CY 2020
City: TUGUEGARAO CITY
Programs or Projects | Location | Total Cost | Date started | Target | Project Status | Total Cost Incurred | No. of
|  |  |  | Completion | % of |  | Extentions, if | REMARKS
|  |  |  | Date | Completion |  | any
| Along Montessory Street , | [6 empty] | -
Leonarda
Along Sanit Louis Village,
Ugac Sur
Along Avida Outlet,
Carig Sur
Along Arao Street,
Ugac Sur
Along Tobias Street,
Ugac Sur
Along Carag Street,
Leonarda
Cagayan National High
School
Along Provincial Road
Atulayan Norte
Along San Roque Street,
Pengue-Ruyu
Total |  | 135061078 |  |  | 1.336% | 1804164.86
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Sgd. POTENCIANA I. CAMPOS |  |  |  | Sgd. ATTY. JEFFERSON P. SORIANO
City Budget Officer |  |  |  | City Mayor